Northern Health and Social Care Trust Board Meeting in Public - Cover Sheet

| Subject: | Trust Board Financial Position Report – May 2026 |  |  | Date of Meeting: 25th June 2026 |  |
| --- | --- | --- | --- | --- | --- |
| Prepared By: | Financial Management |  |  |  |  |
| Approved By: | Labhaoise Boyle, Interim Assistant Director of Financial Management |  |  |  |  |
| Presented By: | Stevie Lennon, Interim Director of Finance |  |  |  |  |
| Purpose |  |  |  |  |  |
| To provide an update to Trust Board on the Financial Outturn of the Trust as at Period 2 (May 26). |  |  |  | Approval |  |
|  |  |  |  | Assurance | X |
|  |  |  |  | Update |  |
|  |  |  |  | Noting |  |
| Strategic Objectives |  |  |  |  |  |
| Build Northern Partnerships and Integrate Care | Continue to improve Outcomes & Experience | Deliver value by optimising Resources | Nurture our People, Enable our Talent & Build Our Teams | Improve population Health & address health & social care inequalities |  |
|  |  | x |  |  |  |
| Risk – please note if links to any principal, corporate or divisional risk |  |  |  |  |  |
| 28 | Principle Risk – Failure to Break-even |  |  |  |  |
| Committees/groups where this item has been presented before |  |  |  |  |  |
| N/A |  |  |  |  |  |
| Acronyms |  |  |  |  |  |
| BSO: Business Services Organisation PPE: Personal Protective Equipment DoH: Department of Health FYE: Full Year Effect PHA: Public Health Authority WTE: Whole Time Equivalent SPPG: Strategic Planning & Performance Group FSL: Funded Staff Level FSS: NHSCT Financial Support Services DLS: Directorate of Legal Services ARSS: BSO Accounts Receivable Shared Services OCP: Office of Care & Protection FAS: NHSCT Financial Accounting Services HRPTS: Human Resources, Payroll & MORE: Medicines Optimisation Regional Efficiency Travel System NIMDTA: Northern Ireland Medical & Dental Training Agency EJO: Enforcement of Judgement Office SFMG: System Financial Management Group RRL: Revenue Resource Limit |  |  |  |  |  |
| Executive Summary |  |  |  |  |  |
| The Trust has reported on Monitoring Return for month 2 based on expenditure only as we have not yet received the RRL from the Commissioners. The Financial Planning process is on-going with the DoH, the Trust has identified phase 1 savings of £30.9m. Work is on-going with the SPPG and DoH to finalise a 2026/27 plan. This will include the identification of further savings including a DoH target and the Trust will need to address underlying deficit and manage 2026/27 growth within the final RRL envelope. Financial Position Key deficits remain in MEM and CC, while in MHLDPS there continues to be a financial pressure on High-Cost Placements across all programmes of Care. Savings Total phase 1 savings plan was for £30.9m, currently it is anticipated that, while these savings will be very challenging, they are achievable. Flexible Staffing Total Agency Spend to May 26 was £9.8m of which 16% was off framework. This off framework spend was in Medical Agencies and they are currently going through their transition phase to the new framework. Total Flexible staffing costs year-to-date are £17.1m which is £1.0 m below the same period in 2025/26. |  |  |  |  |  |

TRUST BOARD

FINANCIAL POSITION REPORT – May 26

Prepared & Issued by Finance Department

Contents

Page 5: 	Section 1: Financial Performance Targets 2026/27

Page 6:	Section 2: Financial Position at May 2026

Page 10:	Section 3: Savings Target 2026/27

Page 11:	Section 4: Flexible Staffing Costs at May 2027

Page 16:	Section 5: Key Assumptions & Risks

Section 1: Financial Performance Targets 2026/27

| Financial Performance Targets | RAG STATUS |
| --- | --- |
| - Agree in-year break-even financial plan agreed with SPPG and DoH | R |
| The Trust is working with SPPG and DoH to deliver an agreed Financial Plan for 2026/27, including the required savings to break-even and the actions that the Trust needs to take to achieve this. There will need to be significant effort to achieve a break-even plan and it will need to align with the foundations of the 3-year reset plan. |  |
| - Achieve in-year break-even outturn within allocated Revenue Resource Limit (RRL) | R |
| The Trust is currently forecasting a deficit – the final position of that deficit will be agreed following completion of the Trusts Financial Plan for 2026/27. |  |
| - Achieve 2025/26 Savings Target | G |
| The Trust has identified Phase 1 Savings target of £30.9m, this will require hard work across the Trust to deliver. The assumption at Mth 2 is that full delivery, while challenging, is achievable. |  |
| - Reductions to Agency Spend - Cease all off Framework Social Work Agency 01/04/23 and all Social Work Agency from 01/07/23 - Cease all off Framework Nurse Agency Spend by 15th August 2023 | G |
| All Social Work Agency has ceased and all Off-Framework Agency Spend for Registered Nursing and HCA has ceased. |  |
| - Prompt Payment Target - 95% of suppliers within 30 days | G |
| Trust performance measure indicates that at 1st June 94.95% of invoices have been paid per prompt payment target. |  |

Section 2: Financial Position at May 2026

The Trust has yet to receive allocation from Commissioners and the Monitoring return for May 2026 has been completed on a year-to-date expenditure basis.

The Income and Expenditure position at May 2026 is:

Table 2: 2025/26 Month 2 (May 2026) Income & Expenditure

|  | Actual Expenditure (Mth 2) £’000 |
| --- | --- |
| Pay Expenditure | 129,469 |
| Net Non-Pay Expenditure | 78,806 |
| Total Expenditure | 208,275 |
| Total RRL |  |
| (Surplus) / Deficit at March 26 |  |
| % (Surplus)/Deficit against RRL |  |

This expenditure position is based on

In Year Position

The Year-to-date expenditure position per the Trust Monitoring Returns is £208 million.

Recurrent Position

The estimated opening deficit 2026/27 is £8m. This is before 2026/27 growth, indicative funding and savings retractions set by DoH.

Financial Plan

The Trust continues to work with DoH and SPPG on finalising a Financial Plan for 2026/27. Agreement has been reached on the Trust Phase 1 Savings plan of £30.9m. Identification and approval of additional savings will continue over the next number of months. The Trust will be expected to deliver break-even against the underlying deficit and manage 2026/27 growth within overall RRL limit as a minimum.

Division Financial Position at May 2026

Table 3: 2025/26 Outturn by Division

| Division/Directorate | Expenditure £’000 | Outturn March 2027 £’000 |
| --- | --- | --- |
| Medicine & Emergency Medicine (MEM) | 27,471 |  |
| Surgical & Clinical Services (SCS) | 32,539 |  |
| Community Care (CC) | 44,523 |  |
| Children & Young People (CYP) | 18,339 |  |
| Mental Health, Learning Disability & Psychology (MHLDPS) | 47,913 |  |
| Nursing, Paediatrics, Women & Corporate Services (NPWCS) | 20,130 |  |
| AHPs and Intermediate Care (AHPIC) | 2 |  |
| Medical & Governance (M&G) | 4,390 |  |
| Strategic Planning, Performance & ICT (SPPICT) | 2,731 |  |
| Infrastructure | 2,885 |  |
| Corporate Overheads | 3,228 |  |
| Finance | 2,427 |  |
| Operations Department | 490 |  |
| Human Resources, OD & Corp Comms (HROD) | 1,304 |  |
| Chief Executive & Trust Board | 106 |  |
| Corporate/Cost Pressures (including Covid, WLI, Corp Deficit and deficit funding) | (203) | TBC |
| Totals | 208,275 |  |

This position includes a number of accruals, estimates. The budget is not included as the MMR for Mth 2 has been reported on expenditure only.

Key Financial Issues in each Division are:

- Medicine & Emergency Medicine   – This Division continues to be one of the overall key areas of financial risk to the Trust. The most significant deficits are in Medical and Nursing. Medical, because of agency premium on agency doctors, covering vacant posts and gaps in rotas.  Nursing, because of extended Emergency Department (ED) footprint and Enhanced Care, across a range of wards.

- Surgical & Clinical Services – Key Deficits remain within Surgery, Anaesthetics and Radiology – this is mostly all with respect to medical and nursing staff. Cost drivers within medical and nursing being Utilisation of nursing above budgeted hours and agency premium, on vacant posts. This is offset by vacant posts throughout the Division.

Community Care – The biggest issues in this Division remain 1:1’s / Bespokes and Intermediate Care (Residential Homes, Community Hospitals and IS Beds) and Contingency beds, there is also an overspend on Independent Sector (IS) Domiciliary Care and Direct Payments. However, offset against all of this is an underspend in In House (IH) Domiciliary Care – due to vacancies. As with the Acute Divisions there is an overspend in Nursing Staff – this is both due to utilisation of hours above budget and premium paid to Nurse Agency staff.

- Children & young People – There continues to be pressures within Corporate Parenting mainly driven by increased activity resulting in cost pressures on Children’s expenditure, but this is being offset by surpluses in pay driven by vacant posts in other areas in particular Child & Adolescent Mental Health Services (CAMHS).   Staffing within Children with Disabilities continues to be problematic. The Division was unable to deliver savings targets made challenging by the increase in activity numbers..

- Mental Health, LD & PS - There are still some concerning deficit areas including the continued nursing pressures in Acute Inpatients (including in Inver 4), Bespoke 1:1 packages, High-Cost Placements and discharges/resettlements from Holywell (although SPPG Allocations have eased this pressure). There are also several vacant posts in the Community Mental Health, Community LD and Clinical Psychology Services which are also abating the over-spends.

- Nursing, PWCS – There are still some areas of concern remaining within medics requiring the use of locums to deliver care and B2 catering and domestics pay. Underspends in other areas e.g. women’s services, maternity nursing and a surplus from National Living Wage for Band 2s are offsetting these areas of overspend.

- Other Directorates – Within this there are surpluses in Medicine & Governance and Pharmacy Services and HR, SPPICT and Capital & Infrastructure.

The profile of the expenditure in the Trust on Pay and Non-Pay cumulatively to Month 2 for 2025/26 and 2026/27 is set out below in Chart 1.

Notes: The pay segment is impacted by the number of weeks which fall within the reporting.

Section 3: Savings Target 2026/27

For 2026/27 the identified Savings Plan, at Phase 1, for the year is £33.6m. Forecast is that all savings will be achieved based on current information.

Table 4: Phase 1 Savings Plans 2026/27

| Scheme | 2026/27 Savings Per Plan £’000 | Forecast 2026/27 Achieved at March 26 £’000 | Forecast Savings Yet to Start £’000 | Total Forecast Variance v Plan £’000 | RAG Rating |
| --- | --- | --- | --- | --- | --- |
| Nurse Stabilisation | 4,248 |  | 4,248 | 4,248 |  |
| Medical Workforce | 3,245 |  | 3,245 | 3,245 |  |
| Multi-Disciplinary Agency | 1,010 |  | 1,010 | 1,010 |  |
| Review of Payroll Savings | 1,000 |  | 1,000 | 1,000 |  |
| Workforce Reduction | 1,150 |  | 1,150 | 1,150 |  |
| Recruitment Delays | 250 |  | 250 | 250 |  |
| Transport & Taxis | 100 |  | 100 | 100 |  |
| Over achievement of Pharmacy Rebates | 150 |  | 150 | 150 |  |
| Encompass - paper savings achieved | 125 |  | 125 | 125 |  |
| Further Reduction in Backlog of Maintenance | 275 |  | 275 | 275 |  |
| Pathology Demand Management | 150 |  | 150 | 150 |  |
| 2025/26 Postage Scheme | 65 |  | 65 | 65 |  |
| MORE | 1,600 |  | 1,600 | 1,600 |  |
| Skill Mix Diagnostics | 100 |  | 100 | 100 |  |
| Administration Staffing | 285 |  | 285 | 285 |  |
| Administration, Publications & Postage | 89 |  | 89 | 89 |  |
| Income Generation Schemes | 132 |  | 132 | 132 |  |
| NIMDTA | 250 |  | 250 | 250 |  |
| Funding of Phlebotomy Services | 341 |  | 341 | 341 |  |
| Cellular Pathology | 265 |  | 265 | 265 |  |
| Funding of DECC Services | 212 |  | 212 | 212 |  |
| Care Homes Income Uplift | 1,945 |  | 1,945 | 1,945 |  |
| Other Income Uplift schemes | 160 |  | 160 | 160 |  |
| Stat Residential Homes | 390 |  | 390 | 390 |  |
| Efficiency of Trust Estate | 200 |  | 200 | 200 |  |
| Sustainability | 147 |  | 147 | 147 |  |
| Reducing Conveyancing to ED from Care Homes | 164 |  | 164 | 164 |  |
| Reform of Home Care | 500 |  | 500 | 500 |  |
| Community Hospitals & Statutory Residential Care | 459 |  | 459 | 459 |  |
| Care Homes - EPCO / Falls | 900 |  | 900 | 900 |  |
| Continued Review of High-Cost Placements | 1,000 |  | 1,000 | 1,000 |  |
| Non-Recurrent Adjustments | 10,000 |  | 10,000 | 10,000 |  |
| Grand Total | 30,907 | 0 | 30,907 | 30,907 |  |

All savings are currently estimated to be green until month 3 when a further assessment will be completed against each scheme.

Section 4: Flexible Staffing Costs as at 30th May 2026

The Trust continues to have a high level of spend on Flexible Staffing. Work has been done to move all spend to framework agencies and eliminate off framework spend. In all areas, except Medical Staffing, that work should be complete – with only residual spend remaining, this is likely to be older invoices and coding that will be corrected as the year progresses. The Medical Framework was the last framework to complete, and it is still working through the transitional phase of the roll out of the new contract.

Non-Contract Agency Spend

The level of expenditure on Off Framework expenditure has significantly reduced as part of the process to introduce the new regional framework

Overall, the total Agency spend at 31st May 2026 was £9.8m, of this 16% (£1.6m) was on off-framework Agencies. The majority of this off framework spend was in Medical Agencies.

Table 4: Cumulative Agency Spend March 2026 by Director and Family Group

| Directorate | Contract £’000 | Non-Contract £’000 | Total £’000 |  | Family Group | Contract £’000 | Non-Contract £’000 | Total £’000 | Contract % |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Medicine & EM | 3,781 | 732 | 4,513 |  | Admin & Clerical | 519 | 0 | 519 | 100 |
| Surgical & Clinical Services | 1,555 | 395 | 1,950 |  | AHP | 49 | 0 | 49 | 1000 |
| Community Care | 365 | 0 | 365 |  | Ancillary | 765 | 1 | 766 | 100 |
| Children & Young People | 321 | (13) | 308 |  | Health Care Support | 1,276 | 0 | 1,276 | 100 |
| Mental Health, LD & CWD | 951 | 87 | 1,038 |  | Medical | 2,469 | 1,575 | 4,045 | 61 |
| Nursing, Paeds, Women & CS | 918 | 201 | 1,119 |  | Nursing & Midwifery | 2,513 | 0 | 2,513 | 100 |
| Medical & Governance | 59 | 0 | 59 |  | Other | 19 | 0 | 19 | 100 |
| SPP&ICT | 19 | 0 | 19 |  | P&T (mto) | 27 | 4 | 31 | 87 |
| Infrastructure & Capital | 44 | 0 | 44 |  | Pathology | 51 | 0 | 51 | 100 |
| Finance | 42 | 0 | 42 |  | Pharmacy | 1 | 0 | 1 | 100 |
| Operations Department | 2 | 0 | 2 |  | Radiography | 186 | 0 | 186 | 100 |
| HR | 7 | 0 | 7 |  | Social Care | 380 | 1 | 381 | 100 |
| Other Corporate | 192 | 165 | 357 |  | Social Work | 0 | (14) | (14) | 0 |
| TOTAL | 8,256 | 1,567 | 9,823 |  | TOTAL | 8,256 | 1,567 | 9,823 | 84 |

- Total Spend on Flexible Staffing

The total spend in these areas is summarised below:

Table 5: Flexible Spend at May 26

| Division/Directorate | Cum to May 2026 |  |  |  |  |  | Cum to May 25 £000’s | Movement |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Agency Locum £000’s | Agency Other £000’s | Bank £000’s | Overtime £000’s | Add hrs. £000’s | Totals £000’s |  | £000’s | % |
| Medicine & Emergency Medicine | 1,887 | 2,626 | 682 | 219 | 45 | 5,458 | 5,361 | 97 | 2 |
| Surgical & Clinical Services | 1,172 | 779 | 457 | 368 | 78 | 2,853 | 2,988 | (135) | (5) |
| Community Care | 0 | 365 | 1,635 | 258 | 108 | 2,366 | 2,500 | (134) | (5) |
| Children & Young People | 0 | 308 | 468 | 342 | 51 | 1,169 | 1,079 | 90 | 8 |
| Mental Health, LD & CWD | 397 | 642 | 969 | 145 | 29 | 2,181 | 2,573 | (392) | (15) |
| Medical & Governance | 0 | 59 | 12 | 13 | 12 | 96 | 65 | 31 | 48 |
| Nursing, Paeds, Women’s & Corp Serv. | 424 | 696 | 890 | 114 | 221 | 2,345 | 2,171 | 174 | 8 |
| Others | 164 | 304 | 100 | 49 | 9 | 628 | 1,403 | (775) | (55) |
| TOTALS | 4,044 | 5,779 | 5,213 | 1,508 | 553 | 17,096 | 18,140 | (1,044) | (6) |

Spend has reduced against the same period last year, however this may be due to forecasting adjustments that are not yet posted due to timing issues, and a clearer picture is likely to be available in Month 3.

This report includes both ACTUAL invoices on the system and accruals included in the financial position where it is anticipated that they might be missing. There is no reporting on month 1 – therefore May actual includes accruals not posted in April which is why there is an increase in spend in May v April.

Expenditure on Flexible nursing is £7.5m cumulative to May 2026.  However, the main spend is directly linked to agency spend (as opposed to Bank, Overtime and Additional Hours) which is £3.8m cumulative to May 2026.

Total flexible staffing expenditure is c.13.2% of the total payroll costs.

- Funded Staff Establishments

The Trust has a funded level of staffing posts, which is continually being updated for both recurrent and non-recurrent service developments.

The budgetary process monitors the contracted hours for staff appointed and on our payroll against the budgeted level; this is in line with the Trust’s Standing Financial Instructions.  An adjustment has been made to account for Domiciliary Care staff who work above contracted hours. In addition, where there is a need to avail of medical and non-medical agency cover (for vacancies, sickness, and maternity), this expenditure is indicatively adjusted to provide an estimated level of WTE.  Other backfill flexibility is sourced from bank, overtime and additional hours and this expenditure has also been adjusted to provide an indicative WTE.

Table 6: FSL against Indicative total WTE

| Category | Total FSL (WTE) (including Non recurrent) | Staff on Payroll |  | Agency Indicative (WTE) | Flexible Backfill Indicative | Total Indicative Staff (WTE) | Variance (WTE) |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Perm (WTE) | Temp (WTE) |  | (WTE) |  |  |
| Admin & Clerical | 1,904 | 1,646 | 71 | 75 | 22 | 1,814 | -90 |
| Estates | 181 | 164 | 3 | 3 | 8 | 178 | -3 |
| Medical & Dental | 784 | 690 | 26 | 133 | 16 | 865 | 81 |
| Nursing Registered | 3,133 | 3,040 | 49 | 208 | 210 | 3,507 | 374 |
| Nursing – HCA | 799 | 644 | 5 | 166 | 147 | 962 | 163 |
| Professional/Technical | 1,768 | 1,619 | 82 | 46 | 65 | 1,812 | 44 |
| Social Work | 1,002 | 979 | 21 | 0 | 104 | 1,104 | 102 |
| Social Care | 1,906 | 1,440 | 32 | 53 | 340 | 1,865 | -41 |
| Support Services | 988 | 795 | 16 | 111 | 89 | 1,011 | 23 |
| TOTALS | 12,465 | 11,017 | 305 | 795 | 1,001 | 13,118 | 653 |

Currently the Trust has in the region an additional 653 WTE staff over the funded staffing level; that equates to a staffing level of 5.2% above FSL. Much of this additional staff is in Nursing Staff.

Whilst maternity and sickness backfill will account for the majority of this, there will be a small number of staff who have been appointed because of:

- Career breaks or peripatetic appointments.

- Advancement appointment where funding has not yet been received from the Commissioner but is confirmed (timing delay).

- Additional staffing in respect of encompass.

Section 5: Key Assumptions and Risks

A number of financial assumptions and risks were made in relation to the Financial Plan for 2025/26 and also with regard to the overall financial position.

- The Financial Plan for 2026/27 has not been agreed by SPPG, it is clear that there will need to be significant savings delivered in 2026/27 – including phase 1 savings of £30.9m. The achievement of these savings and additional savings still to be agreed with SPPG and DoH will be critical to achievement of Financial Targets in 2026/27.

- The Trust continues to experience vacancies across critical professional staff. As a result, there is a reliance on a range of Agency Staff, some of whom are high cost. This continues to drive a financial pressure, it is planned that these will be mitigated through the Regional Frameworks and the Agency Reduction groups as well as the Trust Agency Reduction groups. Delivery from these groups is critical to achievement of financial targets in 2026/27.

- There continues to be pressures across the unscheduled care pathway and the run through of that into Community Services. Managing these pressures continues to pressure the Trusts Finances and therefore the achievement of financial targets for 2026/27.

- There continues to be high acuity in Care Homes placements, and this is leading to an increased number of High-Cost Placements which is continuing to put pressure on costs.

- Cost pressures continue to be raised by providers in the Independent Sector with regard to the impact of the National Minimum Wage in Social settings, and other inflationary pressures i.e. within Nursing and Residential Care settings and with Domiciliary Care providers.  The Trust continues to liaise with Providers to quantify and contain this pressure, but National Living Wage (NLW) uplifts have been applied to Nursing & Residential, Community & Voluntary and Supported Living Providers.

- Several job evaluations are pending and will if successful impact on both the Trust recurrent position and the provision of arrears. From 2022/23 it has been agreed regionally that the PSNI holiday and sickness accrual will now be recognised in the Trust Accounts as a provision.

- The HRPTS (Payroll) has a range of outstanding issues, which impact on our current position. It is understood that the payroll system requires a few ‘fixes’ in order that these issues are corrected and fit for purpose.  The Trust continues to liaise with the BSO Customer Forum to drive these issues forward. Accruals are being carried with respect to these issues.

- We are looking at changes to the Finance Report over the next number of months to focus on key areas, such as staffing costs. These changes will start to be actioned from Month 3 onwards.

not achievable.